## Product Backlog
BI - Product Backlog
sprint/horas remanescentes
| Estimativa | Fator de | Estimativa | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Descrição | Inicial | Ajuste | Ajustada | 156.75 | 126.65 | 94.85 | 61.8 | 15 | 18 | 46.8 | 18 | 32.4 | 8.4
Análise e desenho da solução | 8 | 0.1 | 8.8 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentação | 4 | 0.1 | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Web Services
Desenvolvimento da estrutura básica do projeto | 4 | 0.1 | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integração com a base de dados | 1 | 0.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementação do REST | 2 | 0.2 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Análise da lógica existente | 1.5 | 0.2 | 1.8 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Criação de testes unitários | 1.5 | 0.2 | 1.8 | 1.8 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lógicas | 8 | 0.2 | 9.6 | 9.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-1 |  |  | 34.3 | 31.9 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lógicas | 23 | 0.2 | 27.6 | 27.6 | 27.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Criptografia dos dados | 6 | 0.2 | 7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Diagrama UML | 2 | 0.2 | 2.4 | 2.4 | 2.4 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Criação de testes unitários | 1.5 | 0.2 | 1.8 | 1.8 | 1.8 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testes | 2 | 0.2 | 2.4 | 2.4 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-2 |  |  | 41.4 | 34.2 | 34.2 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Release-1 |  |  | 75.7 | 66.1 | 36 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aplicação Desktop
Desenvolvimento da estrutura básica do projeto | 4 | 0.1 | 4.4 | 4.4 | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integração com o Web Services | 2 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Criação de testes unitários | 1.5 | 0.1 | 1.65 | 1.65 | 1.65 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lógicas | 15 | 0.2 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Diagrama UML | 2 | 0.2 | 2.4 | 2.4 | 2.4 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testes | 2 | 0.2 | 2.4 | 2.4 | 2.4 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-3 |  |  | 28.85 | 28.85 | 28.85 | 28.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design | 16 | 0.2 | 19.2 | 19.2 | 19.2 | 19.2 | 19.2 | 0 | 0 | 0 | 0 | 0 | 0
Autenticação e segurança | 16 | 0.2 | 19.2 | 19.2 | 19.2 | 19.2 | 19.2 | 0 | 0 | 0 | 0 | 0 | 0
Diagrama UML | 4 | 0.2 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 0 | 0 | 0 | 0 | 0 | 0
Criação de testes unitários | 3 | 0.2 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-4 |  |  | 46.8 | 46.8 | 46.8 | 46.8 | 46.8 | 0 | 0 | 0 | 0 | 0 | 0
Refactoring | 3 | 0.1 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0
Documentação | 3 | 0.1 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0
Diagrama UML | 4 | 0.2 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8
Criação de testes unitários | 3 | 0.2 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6
Sprint-5 |  |  | 15 | 15 | 15 | 15 | 15 | 15 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4
Release-2 |  |  | 90.65 | 90.65 | 90.65 | 90.65 | 61.8 | 15 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4
Opção de Intercompany | 8 | 0.2 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 0 | 0 | 0 | 0
Sprint-6 |  |  | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 0 | 0 | 0
Release-3 |  |  | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 0 | 0 | 0
Mapear campos do PL/SQL | 3 | 0.2 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 0 | 0 | 0
Criar modelo de dados | 2 | 0.2 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 0 | 0 | 0
Fechamento batch | 3 | 0.2 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 0 | 0 | 0
Criar Beans | 8 | 0.2 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 0 | 0 | 0
Criar design | 8 | 0.2 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 0 | 0 | 0
Sprint-7 |  |  | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 0 | 0 | 0
Release-4 |  |  | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 0 | 0 | 0
Exportar Ranking para Excel | 8 | 0.2 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 0 | 0
Sprint-8 |  |  | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 0 | 0
Release-5 |  |  | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 0 | 0
Incluir cut-off no fechamento | 8 | 0.2 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 0
Cut-off na Mapa de Vendas | 6 | 0.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 0
Cut-off no Ranking por Gerência | 6 | 0.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 0
Sprint-9 |  |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 0
Release-6 |  |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 0
Product Backlog |  |  | 166.35 | 156.75 | 126.65 | 94.85 | 61.8 | 15 | 18 | 46.8 | 18 | 32.4 | 8.4

## Sprint-1
BI - Sprint-1 Backlog
horas remanescentes até finalização
Descrição | Origem | Responsável | Status | 1 | 2 | 3 | 4
Análise e desenho da solução | Carlos Gomes | Carlos Gomes | Completed | 6 | 4 | 1 | 0 | 0
Tecnologias e frameworks a serem utilizados | Carlos Gomes | Carlos Gomes | Completed | 1 | 0 | 0 | 0 | 0
Criptografia do WebServices - Overview | Carlos Gomes | Carlos Gomes | Completed | 1 | 0 | 0 | 0 | 0
Backlog do Produto | Carlos Gomes | Carlos Gomes | Completed | 3 | 0 | 0 | 0 | 0
Scrum Board | Carlos Gomes | Carlos Gomes | Completed | 0.5 | 0 | 0 | 0 | 0
Diretórios de arquivos | Carlos Gomes | Carlos Gomes | Completed | 0.5 | 0 | 0 | 0 | 0
Versionamento | Carlos Gomes | Carlos Gomes | Completed | 1 | 1 | 0 | 0 | 0
Criação do projeto no eclipse | Carlos Gomes | Carlos Gomes | Completed | 3 | 3 | 0 | 0 | 0
Integração com a base de dados | Carlos Gomes | Carlos Gomes | Completed | 1 | 1 | 1 | 0 | 0
Implementação do REST | Carlos Gomes | Carlos Gomes | Not started | 2 | 2 | 2 | 2 | 2
Análise da lógica existente | Carlos Gomes | Carlos Gomes | Completed | 1.5 | 1.5 | 1.5 | 0 | 0
Criação de testes unitários com JUnit | Carlos Gomes | Carlos Gomes | Not started | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Criar novo schema no BD | Carlos Gomes | Carlos Gomes | Completed | 1 | 1 | 1 | 0 | 0
Lógicas | Carlos Gomes | Carlos Gomes | Completed | 7 | 7 | 7 | 5 | 0
Sprint-1 |  |  |  | 30 | 22 | 15 | 8.5 | 3.5
Note on E5: Not started In progress Completed

## Sprint-2
BI - Sprint-2 Backlog
horas remanescentes até finalização
Descrição | Origem | Responsável | Status | 1 | 2 | 3 | 4 | 5
Persistência na entidade Vendas Líquida | Carlos Gomes | Carlos Gomes | Completed | 9 | 2 | 0 | 0 | 0 | 0
Abatimento de devolução | Carlos Gomes | Carlos Gomes | Completed | 9 | 9 | 4 | 0 | 0 | 0
Consulta de Vendas Líquida | Carlos Gomes | Carlos Gomes | Completed | 9 | 9 | 9 | 4.2 | 0 | 0
Outras lógicas de negócio | Carlos Gomes | Carlos Gomes | Completed | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0
Criptografia dos dados | Carlos Gomes | Carlos Gomes | Not started | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2
Diagrama UML | Carlos Gomes | Carlos Gomes | Not started | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4
Criação de testes unitários com JUnit | Carlos Gomes | Carlos Gomes | Not started | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8
Testes | Carlos Gomes | Carlos Gomes | Completed | 2.4 | 2.4 | 2.4 | 2.4 | 0 | 0
Implementação do REST | Carlos Gomes | Carlos Gomes | Not started | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4
Sprint-2 |  |  |  | 43.8 | 36.8 | 29.8 | 21 | 13.8 | 13.8
Note on E5: Not started In progress Completed

## Sprint-3
BI - Sprint-3 Backlog
horas remanescentes até finalização
Descrição | Origem | Responsável | Status | 1 | 2 | 3 | 4 | 5
Desenvolvimento da estrutura básica do projeto | Carlos Gomes | Carlos Gomes | Completed | 4.4 | 0 | 0 | 0 | 0 | 0
Criação de testes unitários | Carlos Gomes | Carlos Gomes | Not started | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7
Lógicas | Carlos Gomes | Carlos Gomes | Completed | 18 | 13.6 | 4.8 | 0 | 0 | 0
Diagrama UML | Carlos Gomes | Carlos Gomes | Not started | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4
Testes | Carlos Gomes | Carlos Gomes | Completed | 2.4 | 2.4 | 2.4 | 2.4 | 0 | 0
Sprint-3 |  |  |  | 28.9 | 20.1 | 11.3 | 6.5 | 4.1 | 4.1
Note on E5: Not started In progress Completed

## Sprint-4
BI - Sprint-4 Backlog
horas remanescentes até finalização
Descrição | Origem | Responsável | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7
Design | Carlos Gomes | Carlos Gomes | Completed | 19.2 | 12.4 | 5.6 | 0 | 0 | 0 | 0 | 0
Autenticação e segurança | Carlos Gomes | Carlos Gomes | Completed | 19.2 | 19.2 | 19.2 | 19.2 | 12 | 6 | 0 | 0
Diagrama UML | Carlos Gomes | Carlos Gomes | Not started | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8 | 4.8
Criação de testes unitários | Carlos Gomes | Carlos Gomes | Not started | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6
Sprint-4 |  |  |  | 46.8 | 40 | 33.2 | 27.6 | 20.4 | 14.4 | 8.4 | 8.4
Note on E5: Not started In progress Completed

## Sprint-5
BI - Sprint-5 Backlog
horas remanesc.
Descrição | Origem | Responsável | Status | 1 | 2
Refactoring | Carlos Gomes | Carlos Gomes | Completed | 3.3 | 0 | 0
Documentação | Carlos Gomes | Carlos Gomes | Completed | 3.3 | 0 | 0
Diagrama UML | Carlos Gomes | Carlos Gomes | Not started | 4.8 | 4.8 | 4.8
Criação de testes unitários | Carlos Gomes | Carlos Gomes | Not started | 3.6 | 3.6 | 3.6
Sprint-5 |  |  |  | 15 | 8.4 | 8.4
Note on E5: Not started In progress Completed

## Sprint-6
BI - Sprint-6 Backlog
horas remanesc.
Descrição | Origem | Responsável | Status | 1
Refactoring | Carlos Gomes | Carlos Gomes | Completed | 9.6 | 0
Sprint-6 |  |  |  | 9.6 | 0
Note on E5: Not started In progress Completed

## Sprint-7
BI - Sprint-7 Backlog
horas remanescentes
Descrição | Origem | Responsável | Status | 1 | 2 | 3
Mapear campos do PL/SQL | Carlos Gomes | Carlos Gomes | Completed | 3.6 | 0 | 0 | 0
Criar modelo de dados | Carlos Gomes | Carlos Gomes | Completed | 2.4 | 0 | 0 | 0
Fechamento batch | Carlos Gomes | Carlos Gomes | Completed | 3.6 | 0 | 0 | 0
Criar Beans | Carlos Gomes | Carlos Gomes | Completed | 9.6 | 9.6 | 4.6 | 0
Criar design | Carlos Gomes | Carlos Gomes | Completed | 9.6 | 9.6 | 5 | 0
Sprint-7 |  |  |  | 28.8 | 19.2 | 9.6 | 0
Note on E5: Not started In progress Completed

## Sprint-8
BI - Sprint-8 Backlog
horas remanesc.
Descrição | Origem | Responsável | Status | 1
Exportar Ranking para Excel | Carlos Gomes | Carlos Gomes | Completed | 9.6 | 0
Sprint-8 |  |  |  | 9.6 | 0
Note on E5: Not started In progress Completed

## Sprint-9
BI - Sprint-9 Backlog
horas remanescentes
Descrição | Origem | Responsável | Status | 1 | 2 | 3
Incluir cut-off no fechamento | Carlos Gomes | Carlos Gomes | Completed | 9.6 | 2 | 0 | 0
Cut-off na Mapa de Vendas | Carlos Gomes | Carlos Gomes | Completed | 7.2 | 7.2 | 0 | 0
Cut-off no Ranking por Gerência | Carlos Gomes | Carlos Gomes | Completed | 7.2 | 7.2 | 7.2 | 0
Sprint-9 |  |  |  | 24 | 16.4 | 7.2 | 0
Note on E5: Not started In progress Completed