## Planning
Task | Subtask | hrs | hrs
Project specifications |  | 8
| Docs |  | 2
| BPM |  | 4
| BPMn |  | 2
Initial structure (versioning, frameworks, DNS, etc) |  | 11
| DNS creation |  | 1
| Possibility of a new VM for this product |  | 1
| JBoss setup |  | 1
| Versioning with SVN |  | 1
| Project structure on Eclipse |  | 2
| Frameworks setup |  | 4
| Hello world |  | 1
Design |  | 8
| Layout |  | 2
| Style sheet |  | 2
| Templates |  | 2
| PrimeFaces |  | 2
Data modeling |  | 8
| UML diagram |  | 8
Menu |  | 19
| Data modeling |  | 3
| Entity mapping |  | 1
| Models |  | 2
| Unit test |  | 1
| Controllers |  | 8
| Views |  | 4
Access control |  | 29
| Data modeling |  | 3
| Entity mapping |  | 1
| Models |  | 2
| Unit test |  | 1
| Controllers |  | 8
| Password rules |  | 6
| Intranet access request |  | 8
Suppliers |  | 10
| Analyse current program |  | 3
| Data modeling |  | 2
| Necessary changes |  | 2
| Entity mapping |  | 1
| Models |  | 2
Price List |  | 19
| Data modeling |  | 3
| Entity mapping |  | 1
| Models |  | 2
| Unit test |  | 1
| Controllers |  | 8
| Views |  | 4
Refactoring |  | 6
Contracts |  | 19
Payment Terms |  | 10
Materials |  | 10
Material grouping |  | 10
Material grouping by buyer |  | 10
Materials grouping by account |  | 19 |  | Check if it's possible and necessary for this moment.
Unit measure |  | 10
Currencies |  | 10
Exchange rates |  | 10
Cost Center |  | 10
Cost Center grouping |  | 19 |  | Check if it's possible and necessary for this moment.
Approvers |  | 19
Billing / Shippment / Envoice addresses |  | 19
Refactoring |  | 6
Purchase Request |  | 41
| Data modeling |  | 4
| Entity mapping |  | 1
| Models |  | 3
| Unit test |  | 1
| Controllers |  | 16
| Views |  | 16
Items |  | 13
| Unit test |  | 1
| Controllers |  | 8
| Views |  | 4
Notes |  | 8
| Entity mapping |  | 1
| Models |  | 1
| Unit test |  | 1
| Controllers |  | 4
| Views |  | 1
Refactoring |  | 4
Quotations |  | 63
| Data modeling |  | 5
| Entity mapping |  | 2
| Models |  | 2
| Unit test |  | 1
| Controllers |  | 13
| Views |  | 16
| Mail sending |  | 24
Refactoring |  | 3
Approvers selection |  | 17
Approvals |  | 19
| Entity mapping |  | 2
| Models |  | 2
| Unit test |  | 1
| Controllers |  | 12
| Views |  | 2
Refactoring |  | 1
Redirecting to other buyer |  | 6
Puchase Order generation |  | 34
Refactoring |  | 4
Change history |  | 7
Tests |  | 16
User Training |  | 24
Deployment |  | 16
Help |  | 24
Refactoring |  | 16
Docs |  | 24
Improvements |  | 40
New
Project specifications
Initial structure (versioning, frameworks, DNS, etc)
Design
Data modeling
Menu
Access control
Suppliers
Materials
Price List
Purchase Request
Items
Quotations
Refactoring
Payment Terms
Approvers
Billing / Shippment / Envoice addresses
Notes
Approvers selection
Refactoring
Contracts
Quotations - mail sending
Material grouping
Material grouping by buyer
Materials grouping by account
Unit measure
Currencies
Exchange rates
Cost Center
Cost Center grouping
Approvals
Refactoring
Refactoring, project overview and re-planning
Redirecting to other buyer
Puchase Order generation
Refactoring
Change history
Tests
User Training
Deployment
Help
Refactoring
Docs review
Improvements

## Deadline
SWA-PO - Deadline
| 23/01 | 30/01 | 06/02 | 13/02 | 13/03 | 20/03 | 27/03 | 03/04 | 10/04 | 17/04 | 24/04 | GL
Disponível | 368 | 328 | 288 | 248 | 208 | 168 | 128 | 96 | 56 | 24 | 0 | 0
Expected | 632.5 | 575 | 517.5 | 460 | 402.5 | 345 | 287.5 | 230 | 172.5 | 115 | 57.5 | 0
Realized | 632.5 | 574.2 | 558.2 | 541.2 | 518.2 | 457 | 386.4 | 349.8 | 239.2 | 111.1 | 57.5 | 0
[13 empty] | Realizado | 632.5
[13 empty] | Disp.GL | 632.5
[13 empty] | Falta | 0
111.1

## Product Backlog
SWA-PO - Product Backlog
sprint/hours work remaining until completion
| Initial | Adjustment | Adjusted | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | GL | 10 | 11
Description | Estimate | Factor | Estimate | 746.9 | 655.6 | 518.4 | 464.2 | 304.7 | 293.7 | 239.8 | 225.5 | 176 | 114.4 | 114.4 | 114.4 | 114.4 | Concluído
Project specifications | 8 | 0.1 | 8.8 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Initial structure (versioning, frameworks, DNS, etc) | 11 | 0.1 | 12.1 | 12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Design | 8 | 0.1 | 8.8 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Data modeling | 8 | 0.1 | 8.8 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Menu | 19 | 0.1 | 20.9 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Access control | 29 | 0.1 | 31.9 | 31.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Sprint-1 |  |  | 91.3 | 91.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Suppliers | 10 | 0.1 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Materials | 10 | 0.1 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Price List | 19 | 0.1 | 20.9 | 20.9 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Purchase Request | 41 | 0.1 | 45.1 | 45.1 | 45.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Items | 13 | 0.1 | 14.3 | 14.3 | 14.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Quotations | 39 | 0.1 | 42.9 | 42.9 | 42.9 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Sprint-2 |  |  | 145.2 | 145.2 | 145.2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Refactoring | 6 | 0.1 | 6.6 | 6.6 | 6.6 | 6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Payment Terms | 10 | 0.1 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Approvers | 19 | 0.1 | 20.9 | 20.9 | 20.9 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Billing / Shippment / Envoice addresses | 19 | 0.1 | 20.9 | 20.9 | 20.9 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Notes | 8 | 0.1 | 8.8 | 8.8 | 8.8 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Approvers selection | 17 | 0.1 | 18.7 | 18.7 | 18.7 | 18.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Sprint-3 |  |  | 86.9 | 86.9 | 86.9 | 86.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Release-1 |  |  | 323.4 | 323.4 | 232.1 | 94.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Approvers |  |  |  | 0 | 0 | 0 | 17.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Billing / Shippment / Envoice addresses |  |  |  | 0 | 0 | 0 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Approvers selection |  |  |  | 0 | 0 | 0 | 18.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Refactoring | 6 | 0.1 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Contracts | 19 | 0.1 | 20.9 | 20.9 | 20.9 | 20.9 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Quotations - mail sending | 24 | 0.1 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Material grouping | 10 | 0.1 | 11 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Material grouping by buyer | 10 | 0.1 | 11 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Materials grouping by account | 19 | 0.1 | 20.9 | 20.9 | 20.9 | 20.9 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Sprint-4 |  |  | 96.8 | 96.8 | 96.8 | 96.8 | 137.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Unit measure | 10 | 0.1 | 11 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Currencies | 10 | 0.1 | 11 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Exchange rates | 10 | 0.1 | 11 | 11 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Sprint-5 |  |  | 33 | 33 | 33 | 33 | 33 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Cost Center | 10 | 0.1 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Cost Center grouping | 19 | 0.1 | 20.9 | 20.9 | 20.9 | 20.9 | 20.9 | 20.9 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Approvals | 19 | 0.1 | 20.9 | 20.9 | 20.9 | 20.9 | 20.9 | 20.9 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Refactoring | 1 | 0.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Sprint-6 |  |  | 53.9 | 53.9 | 53.9 | 53.9 | 53.9 | 53.9 | 53.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Release-2 |  |  | 183.7 | 183.7 | 183.7 | 183.7 | 224.4 | 64.9 | 53.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Refactoring, project overview and re-planning | 7 | 0.1 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Redirecting to other buyer | 6 | 0.1 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Sprint-7 |  |  | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Release-3 |  |  | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | %
Puchase Order generation | 34 | 0.1 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 0 | 0 | 0 | 0 | 0 | 100 | %
Refactoring | 4 | 0.1 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 100 | %
Change history | 7 | 0.1 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 0 | 0 | 0 | 0 | 0 | 100 | %
Sprint-8 |  |  | 49.5 | 49.5 | 49.5 | 49.5 | 49.5 | 49.5 | 49.5 | 49.5 | 49.5 | 0 | 0 | 0 | 0 | 0 | 100 | %
Tests | 16 | 0.1 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 0 | 0 | 0 | 0 | 100 | %
User Training | 24 | 0.1 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 0 | 0 | 0 | 0 | 100 | %
Deployment | 16 | 0.1 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 0 | 0 | 0 | 0 | 100 | %
Sprint-9 |  |  | 61.6 | 61.6 | 61.6 | 61.6 | 61.6 | 61.6 | 61.6 | 61.6 | 61.6 | 61.6 | 0 | 0 | 0 | 0 | 100 | %
Release-4 |  |  | 111.1 | 111.1 | 111.1 | 111.1 | 111.1 | 111.1 | 111.1 | 111.1 | 111.1 | 61.6 | 0 | 0 | 0 | 0 | 100 | %
Help | 24 | 0.1 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 0 | %
Refactoring | 16 | 0.1 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 0 | %
Docs review | 24 | 0.1 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 0 | %
Sprint-10 |  |  | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 0 | %
Release-5 |  |  | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 70.4 | 0 | %
Improvements | 40 | 0.1 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 0 | %
Sprint-11 |  |  | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 0 | %
Release-6 |  |  | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 0 | %
Product Backlog |  |  | 746.9 | 746.9 | 655.6 | 518.4 | 464.2 | 304.7 | 293.7 | 239.8 | 225.5 | 176 | 114.4 | 114.4 | 114.4 | 114.4 | 84.6834 | %
Expected |  |  |  | 746.9 | 655.6 | 510.4 | 464.2 | 304.7 | 293.7 | 239.8 | 225.5 | 176 | 114.4 | 114.4 | 44 | 0

## Sprint-9
SWA-PO - Sprint-9 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3 | 4 | 5 | 6
Tests | Carlos Gomes | Carlos Gomes | Completed | 17.6 | 10 | 10 | 10 | 0 | 0 | 0
User Training | Carlos Gomes | Carlos Gomes | Completed | 26.4 | 26.4 | 13 | 0 | 0 | 0 | 0
Deployment | Carlos Gomes | Carlos Gomes | Completed | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 10 | 0
Sprint-9 |  |  |  | 61.6 | 54 | 40.6 | 27.6 | 17.6 | 10 | 0
Expected |  |  |  | 61.6 | 45.6 | 29.6 | 13.6 | 0
Note on E5: Not started In progress Completed
Note on F5: 27/04/2015
Note on G5: 28/04/2015
Note on H5: 29/04/2015
Note on I5: 30/04/2015
Note on J5: 01/05/2015
Note on K5: 02/05/2015

## Sprint-8
SWA-PO - Sprint-8 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3
Puchase Order generation | Carlos Gomes | Carlos Gomes | Completed | 37.4 | 30 | 15 | 0
Refactoring | Carlos Gomes | Carlos Gomes | Completed | 4.4 | 0 | 0 | 0
Change history | Carlos Gomes | Carlos Gomes | Completed | 7.7 | 3 | 0 | 0
Sprint-8 |  |  |  | 49.5 | 33 | 15 | 0
Expected |  |  |  | 49.5 | 33.5 | 17.5 | 1.5
Note on E5: Not started In progress Completed
Note on F5: 22/04/2015
Note on G5: 23/04/2015
Note on H5: 24/04/2015

## Sprint-7
SWA-PO - Sprint-7 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1
Refactoring, project overview and re-planning | Carlos Gomes | Carlos Gomes | Completed | 7.7 | 0
Redirecting to other buyer | Carlos Gomes | Carlos Gomes | Completed | 6.6 | 0
Sprint-7 |  |  |  | 14.3 | 0
Expected |  |  |  | 14.3 | 0
Note on E5: Not started In progress Completed
Note on F5: 21/04/2015

## Sprint-6
SWA-PO - Sprint-6 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3 | 4
Cost Center | Carlos Gomes | Carlos Gomes | Completed | 11 | 0 | 0 | 0 | 0
Cost Center grouping | Carlos Gomes | Carlos Gomes | Completed | 20.9 | 5 | 5 | 0 | 0
Approvals | Carlos Gomes | Carlos Gomes | Completed | 20.9 | 20.9 | 10 | 0 | 0
Refactoring | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 0 | 0 | 0
Sprint-6 |  |  |  | 53.9 | 27 | 15 | 0 | 0
Expected |  |  |  | 53.9 | 37.9 | 21.9 | 5.9 | 0
Note on E5: Not started In progress Completed
Note on F5: 17/04/2015
Note on G5: 18/04/2015
Note on H5: 20/04/2015

## Sprint-5
SWA-PO - Sprint-5 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1
Unit measure | Carlos Gomes | Robson Nunes | Completed | 11 | 0
Currencies | Carlos Gomes | Robson Nunes | Completed | 11 | 0
Exchange rates | Carlos Gomes | Carlos Gomes | Completed | 11 | 0
Sprint-5 |  |  |  | 33 | 0
Expected |  |  |  | 33 | 0
Note on E5: Not started In progress Completed
Note on F5: 16/04/2015

## Sprint-4
SWA-PO - Sprint-4 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Approvers
Data modeling | Carlos Gomes | Carlos Gomes | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Entity mapping | Carlos Gomes | Robson Nunes | Completed | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Models | Carlos Gomes | Robson Nunes | Completed | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unit test | Carlos Gomes | Robson Nunes | Completed | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Controllers | Carlos Gomes | Carlos Gomes | Completed | 8.8 | 8.8 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Views | Carlos Gomes | Carlos Gomes | Completed | 4.4 | 4.4 | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0
Billing / Shippment / Envoice addresses
Data modeling | Carlos Gomes | Carlos Gomes | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Entity mapping | Carlos Gomes | Robson Nunes | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Models | Carlos Gomes | Robson Nunes | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unit test | Carlos Gomes | Robson Nunes | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Controllers | Carlos Gomes | Robson Nunes | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Views | Carlos Gomes | Robson Nunes | Completed | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes | Carlos Gomes | Robson Nunes | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Approvers selection
Entity mapping | Carlos Gomes | William Ata | Completed | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unit test | Carlos Gomes | William Ata | Completed | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Controllers | Carlos Gomes | William Ata | Completed | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 0 | 0 | 0
Views | Carlos Gomes | William Ata | Completed | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 0 | 0 | 0
Refactoring | Carlos Gomes | Carlos Gomes | Completed | 6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts | Carlos Gomes | Carlos Gomes | Completed | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quotations - mail sending | Carlos Gomes | Robson Nunes | Completed | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 0 | 0 | 0
Material grouping | Carlos Gomes | Carlos Gomes | Completed | 11 | 11 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Material grouping by buyer | Carlos Gomes | Carlos Gomes | Completed | 11 | 11 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Materials grouping by account | Carlos Gomes | Carlos Gomes | Completed | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-4 |  |  |  | 137.5 | 84.7 | 65.4 | 53.3 | 48.9 | 48.9 | 42.9 | 0 | 0 | 0
Expected |  |  |  | 137.5 | 121.5 | 105.5 | 89.5 | 73.5 | 57.5 | 41.5 | 25.5 | 9.5 | 0
Note on E5: Not started In progress Completed
Note on F5: 07/04/2015
Note on G5: 08/04/2015
Note on H5: 09/04/2015
Note on I5: 10/04/2015
Note on J5: 13/04/2015
Note on K5: 14/04/2015
Note on L5: 15/04/2015

## Sprint-3
SWA-PO - Sprint-3 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3 | 4 | 5 | 6
Refactoring | Carlos Gomes | Carlos Gomes | Completed | 6.6 | 0 | 0 | 0 | 0 | 0 | 0
Payment Terms
Analyse current program | Carlos Gomes | Carlos Gomes | Completed | 3.3 | 0 | 0 | 0 | 0 | 0 | 0
Data modeling | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 0 | 0 | 0 | 0 | 0 | 0
Necessary changes | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 0 | 0 | 0 | 0 | 0 | 0
Entity mapping | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 0 | 0 | 0 | 0 | 0 | 0
Models | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 0 | 0 | 0 | 0 | 0 | 0
Approvers
Data modeling | Carlos Gomes | Carlos Gomes | Completed | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0
Entity mapping | Carlos Gomes | Robson Nunes | Not started | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0
Models | Carlos Gomes | Robson Nunes | Not started | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 0
Unit test | Carlos Gomes | Robson Nunes | Not started | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0
Controllers | Carlos Gomes | Carlos Gomes | Not started | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 0
Views | Carlos Gomes | Carlos Gomes | Not started | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 0
Billing / Shippment / Envoice addresses
Data modeling | Carlos Gomes | Carlos Gomes | Completed | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0
Entity mapping | Carlos Gomes | Robson Nunes | Completed | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0
Models | Carlos Gomes | Robson Nunes | Completed | 2.2 | 2.2 | 2.2 | 0 | 0 | 0 | 0
Unit test | Carlos Gomes | Robson Nunes | Completed | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0
Controllers | Carlos Gomes | Robson Nunes | Completed | 8.8 | 8.8 | 8.8 | 0 | 0 | 0 | 0
Views | Carlos Gomes | Robson Nunes | In progress | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 0
Notes | Carlos Gomes | Robson Nunes | Completed | 8.8 | 8.8 | 8.8 | 8.8 | 0 | 0 | 0
Approvers selection
Entity mapping | Carlos Gomes | Carlos Gomes | Not started | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0
Unit test | Carlos Gomes | Carlos Gomes | Not started | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0
Controllers | Carlos Gomes | Carlos Gomes | Not started | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 0
Views | Carlos Gomes | Carlos Gomes | Not started | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 0
Sprint-3 |  |  |  | 86.9 | 69.3 | 62.7 | 49.5 | 40.7 | 40.7 | 0
Expected |  |  |  | 86.9 | 71.9 | 56.9 | 41.9 | 26.9 | 11.9 | -3.1
Note on E5: Not started In progress Completed
Note on F5: 30/03/2015
Note on G5: 31/03/2015
Note on H5: 01/04/2015
Note on I5: 02/04/2015
Note on J5: 03/04/2015
Note on K5: 06/04/2015

## Sprint-2
SWA-PO - Sprint-2 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Suppliers
Analyse current program | Carlos Gomes | Carlos Gomes | Completed | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data modeling | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Necessary changes | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Entity mapping | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Models | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 2.2 | 2.2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials
Analyse current program | Carlos Gomes | Carlos Gomes | Completed | 3.3 | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data modeling | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Necessary changes | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Entity mapping | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0
Models | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0
Price List
Data modeling | Carlos Gomes | Carlos Gomes | Completed | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 0 | 0 | 0 | 0
Entity mapping | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0
Models | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 0 | 0 | 0 | 0
Unit test | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0
Controllers | Carlos Gomes | Carlos Gomes | Completed | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 0 | 0 | 0 | 0
Views | Carlos Gomes | Carlos Gomes | Completed | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 0
Purchase Request
Data modeling | Carlos Gomes | Carlos Gomes | Completed | 4.4 | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Entity mapping | Carlos Gomes | Robson Nunes | Completed | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Models | Carlos Gomes | Robson Nunes | Completed | 3.3 | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unit test | Carlos Gomes | Robson Nunes | Completed | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0
Controllers | Carlos Gomes | Robson Nunes | Completed | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 13 | 10 | 10 | 10 | 10 | 10 | 0
Views | Carlos Gomes | Robson Nunes | Completed | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 12 | 10 | 10 | 10 | 10 | 10 | 0
Items
Unit test | Carlos Gomes | Robson Nunes | Completed | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0
Controllers | Carlos Gomes | Robson Nunes | Completed | 8.8 | 8.8 | 8.8 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Views | Carlos Gomes | Robson Nunes | Completed | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 0
Quotations
Data modeling | Carlos Gomes | Carlos Gomes | Completed | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Entity mapping | Carlos Gomes | Robson Nunes | Completed | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Models | Carlos Gomes | Robson Nunes | Completed | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unit test | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0
Controllers | Carlos Gomes | Robson Nunes | Completed | 14.3 | 14.3 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Views | Carlos Gomes | Robson Nunes | In progress | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 13 | 11 | 9 | 9 | 9 | 9 | 9 | 0
Sprint-2 |  |  |  | 145.2 | 136.4 | 122.2 | 105.7 | 85.7 | 80.1 | 67.9 | 60.9 | 55.4 | 37.8 | 37.8 | 37.8 | 0
Expected |  |  |  | 145.2 | 130.2 | 115.2 | 100.2 | 85.2 | 70.2 | 55.2 | 40.2 | 25.2 | 10.2 | -4.8 | -19.8 | -34.8
Note on E5: Not started In progress Completed
Note on F5: 12/03/2015
Note on G5: 13/03/2015
Note on H5: 16/03/2015
Note on I5: 17/03/2015
Note on J5: 18/03/2015
Note on K5: 19/03/2015
Note on L5: 20/03/2015
Note on M5: 23/03/2015
Note on N5: 24/03/2015
Note on O5: 25/03/2015
Note on P5: 26/03/2015
Note on Q5: 27/03/2015

## Sprint-1
SWA-PO - Sprint-1 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Docs | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PPM | Carlos Gomes | Carlos Gomes | Completed | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BPMn | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNS creation | Carlos Gomes | William Rodrigues | Completed | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Possibility of a new VM for this product | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
JBoss setup | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Versioning with SVN | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project structure on Eclipse | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Frameworks setup | Carlos Gomes | Carlos Gomes | Completed | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
POC | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Layout | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Style sheet | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Templates | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PrimeFaces | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UML diagram | Carlos Gomes | Carlos Gomes | Completed | 8.8 | 8.8 | 8.8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Menu - Data modeling | Carlos Gomes | Carlos Gomes | Completed | 3.3 | 3.3 | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Entity mapping | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Models | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unit test | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0 | 0 | 0
Controllers | Carlos Gomes | Carlos Gomes | Completed | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Views | Carlos Gomes | Carlos Gomes | Completed | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Access Control - Data modeling | Carlos Gomes | Carlos Gomes | Completed | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Entity mapping | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Models | Carlos Gomes | Carlos Gomes | Completed | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unit test | Carlos Gomes | Carlos Gomes | Completed | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0 | 0 | 0
Controllers | Carlos Gomes | Carlos Gomes | Completed | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 7.4 | 0 | 0 | 3 | 0 | 0 | 0
Password rules | Carlos Gomes | Carlos Gomes | Completed | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6 | 2 | 0 | 0 | 0 | 0
Intranet access request | Carlos Gomes | Renato Stoll | Not started | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 0 | 0 | 0
Sprint-1 |  |  |  | 91.3 | 81.4 | 68.2 | 57.8 | 49.5 | 33 | 25 | 17 | 13 | 14 | 0 | 0 | 0
Expected |  |  |  | 91.3 | 83.3 | 75.3 | 67.3 | 59.3 | 51.3 | 43.3 | 35.3 | 27.3 | 19.3 | 11.3 | 3.3 | 0
Note on E5: Not started In progress Completed
Note on F5: 26/01/2015
Note on G5: 27/01/2015
Note on H5: 28/01/2015
Note on I5: 29/01/2015
Note on J5: 30/01/2015
Note on K5: 05/02/2015
Note on L5: 06/02/2015
Note on M5: 09/02/2015
Note on N5: 10/02/2015
Note on O5: 11/02/2015