## Deadline
Política de Vendas - Deadline
| 24/07 | 31/07 | 07/08 | 14/08 | 21/08 | 28/08 | 04/09 | 11/09 | 18/09 | 25/09 | 01/10
Disponível | 368 | 328 | 288 | 248 | 208 | 168 | 128 | 96 |  |  | 56
Expected | 349.8 | 319.8 | 289.8 | 259.8 | 199.8 | 139.8 | 79.8 | 19.8 | 0
Realized | 349.8 | 319.8 | 289.8 | 250.8

## Product Backlog
Política de Vendas - Product Backlog
sprint/hours work remaining until completion
| Initial | Adjustment | Adjusted | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Description | Estimate | Factor | Estimate | 349.8 | 330 | 303.6 | 268.4 | 250.8 | 250.8 | 250.8 | 250.8 | 250.8 | 250.8 | 250.8 | 250.8 | 250.8
Project specifications | 12 | 0.1 | 13.2 | 13.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kick-off | 2 | 0.1 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UX analysis | 4 | 0.1 | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-1 |  |  | 19.8 | 19.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prototyping | 24 | 0.1 | 26.4 | 26.4 | 26.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-2 |  |  | 26.4 | 26.4 | 26.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data modeling | 24 | 0.1 | 26.4 | 26.4 | 26.4 | 26.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Additional docs | 8 | 0.1 | 8.8 | 8.8 | 8.8 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-3 |  |  | 35.2 | 35.2 | 35.2 | 35.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DB scripts | 8 | 0.1 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Beta datas load | 4 | 0.1 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Workflow definition | 4 | 0.1 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-4 |  |  | 17.6 | 17.6 | 17.6 | 17.6 | 17.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2B - Actual code removal | 8 | 0.1 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8
B2B - PV validations | 30 | 0.1 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
Sprint-5 |  |  | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8
Release-1 |  |  | 140.8 | 140.8 | 121 | 94.6 | 59.4 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8 | 41.8
B2B - Screens | 30 | 0.1 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
Sprint-6 |  |  | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
B2B - Adjusts for new workflow | 30 | 0.1 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
Sprint-7 |  |  | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
B2B - Logs | 18 | 0.1 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8
Sprint-8 |  |  | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8
BI - Entity mapping and models | 4 | 0.1 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4
BI - Initial structure | 2 | 0.1 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
BI - Search | 18 | 0.1 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8 | 19.8
Sprint-9 |  |  | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4
BI - New | 30 | 0.1 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
Sprint-10 |  |  | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
Release-2 |  |  | 145.2 | 145.2 | 145.2 | 145.2 | 145.2 | 145.2 | 145.2 | 145.2 | 145.2 | 145.2 | 145.2 | 145.2 | 145.2 | 145.2
BI - Approvals | 30 | 0.1 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
Sprint-11 |  |  | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
BI - Change History | 12 | 0.1 | 13.2 | 13.2 | 13.2 | 13.2 | 13.2 | 13.2 | 13.2 | 13.2 | 13.2 | 13.2 | 13.2 | 13.2 | 13.2 | 13.2
BI - User trainning | 8 | 0.1 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8
Documentation | 8 | 0.1 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8
Sprint-12 |  |  | 30.8 | 30.8 | 30.8 | 30.8 | 30.8 | 30.8 | 30.8 | 30.8 | 30.8 | 30.8 | 30.8 | 30.8 | 30.8 | 30.8
Release-3 |  |  | 63.8 | 63.8 | 63.8 | 63.8 | 63.8 | 63.8 | 63.8 | 63.8 | 63.8 | 63.8 | 63.8 | 63.8 | 63.8 | 63.8
Product Backlog |  |  | 349.8 | 349.8 | 330 | 303.6 | 268.4 | 250.8 | 250.8 | 250.8 | 250.8 | 250.8 | 250.8 | 250.8 | 250.8 | 250.8
Expected |  |  |  | 349.8 | 330 | 303.6 | 268.4 | 250.8 | 209 | 176 | 143 | 123.2 | 96.8 | 63.8 | 30.8 | 0

## Sprint-5
Política de Vendas - Sprint-5 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
B2B - Actual code removal | Carlos Gomes | Carlos Gomes | In progress | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
B2B - PV validations | Carlos Gomes | Carlos Gomes | Not started | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Sprint-5 |  |  |  | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38
Expected |  |  |  | 38 | 32 | 26 | 20 | 14 | 8 | 2 | 0
Note on E5: Not started In progress Completed

## Sprint-9
Política de Vendas - Sprint-9 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
BI - Entity mapping and models | Carlos Gomes | William Atamanchuk | Not started | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BI - Initial structure | Carlos Gomes | William Atamanchuk | Not started | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
BI - Search | Carlos Gomes | William Atamanchuk | Not started | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
Sprint-9 |  |  |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
Expected |  |  |  | 24 | 18 | 12 | 6 | 0 | -6 | -12 | 0
Note on E5: Not started In progress Completed

## Sprint-1
Política de Vendas - Sprint-1 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3 | 4
Project specifications | Carlos Gomes | Carlos Gomes | Completed | 12 | 6 | 0 | 0
Kick-off | Carlos Gomes | Carlos Gomes | Completed | 2 | 2 | 2 | 0
UX analysis | Carlos Gomes | Carlos Gomes | Completed | 4 | 4 | 4 | 0
Sprint-1 |  |  |  | 18 | 12 | 6 | 0
Expected |  |  |  | 18 | 12 | 6 | 0
Note on E5: Not started In progress Completed

## Sprint-2
Política de Vendas - Sprint-2 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3 | 4 | 5
Prototyping | Carlos Gomes | Carlos Gomes | Completed | 24 | 18 | 12 | 6 | 0
Sprint-2 |  |  |  | 24 | 18 | 12 | 6 | 0
Expected |  |  |  | 24 | 18 | 12 | 6 | 0
Note on E5: Not started In progress Completed

## Sprint-3
Política de Vendas - Sprint-3 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7
Data modeling | Carlos Gomes | Carlos Gomes | Completed | 24 | 18 | 12 | 6 | 0 | 0 | 0
Additional docs | Carlos Gomes | Carlos Gomes | Completed | 8 | 8 | 8 | 8 | 8 | 2 | 0
Sprint-3 |  |  |  | 32 | 26 | 20 | 14 | 8 | 2 | 0
Expected |  |  |  | 32 | 26 | 20 | 14 | 8 | 2 | 0
Note on E5: Not started In progress Completed

## Sprint-4
Política de Vendas - Sprint-4 Backlog
hours of working remaining until completition
Description | Originator | Responsible | Status | 1 | 2 | 3 | 4
DB scripts | Carlos Gomes | Carlos Gomes | Completed | 8 | 2 | 0 | 0
Beta datas load | Carlos Gomes | Carlos Gomes | Completed | 4 | 4 | 0 | 0
Workflow definition | Carlos Gomes | Carlos Gomes | Completed | 4 | 4 | 4 | 0
Sprint-4 |  |  |  | 16 | 10 | 4 | 0
Expected |  |  |  | 16 | 10 | 4 | 0
Note on E5: Not started In progress Completed